## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2191-swen-261-07-a SWENTWOSIXTYFUN
Testing Team Name | 2191-swen-261-07-b Discount Ostrich

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 Cross Team | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12 |  | djk; 11/21
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12 |  | djk; 11/21
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12 |  | djk; 11/21
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12 |  | djk; 11/21
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12 |  | djk; 11/21
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12 |  | djk; 11/21
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12 |  | djk; 11/21
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | djk; 10/17/19 |  | bmt; 11/5/19 |  | UD;11/12;starting a game sometimes doesn't work because of signout issues |  | djk; 11/21;starting a game after signing out does not work properly
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | djk; 10/17/19 |  |  |  | UD;11/12 |  | djk; 11/21
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | djk; 10/17/19; Returns the player to the sign in screen rather than the home screen chp; 10/17/19 |  |  |  | UD;11/12 |  | djk; 11/21
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | djk; 10/17/19; Does not work with a space in the username of your opponent djk;10/17/19 |  |  |  | UD;11/12 |  | djk; 11/21
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | djk; 10/17/19 |  |  |  | UD;11/12 |  | djk; 11/21
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | djk; 10/17/19 |  |  |  | UD;11/12 |  | djk; 11/21
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | djk; 10/17/19 |  |  |  | UD;11/12 |  | djk; 11/21
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | djk; 10/17/19 |  |  |  | UD;11/12 |  | djk; 11/21
As a Player I want to choose a checker to move to a new location in order to complete a play. | Given that I am in a game when it is my turn then I should be able to move a checker from my top row of pieces to a diagonally adjacent piece. | [5 empty] | UD;11/12;Pieces can be moved backwards |  | djk; 11/21
| Given that I have made a simple move when it is my turn then I expect to be able to either backup my move or submit my turn. | [5 empty] | UD;11/12 |  | djk; 11/21
| Given that I have made a valid simple move when it is my turn then I expect to see a message notifying me that my move was valid. | [5 empty] | UD;11/12 |  | djk; 11/21
| Given that I have made an invalid simple move when it is my turn then I expect to see a message notifying me that my move was invalid. | [5 empty] | UD;11/12; We can make invalid moves like moving a piece backward, chaining simple moves and it is not marked as invalid. |  | djk; 11/21
| Given that I have submitted my turn when I am satisfied with my turn then I expect the other player to be able to play their turn. | [5 empty] | UD;11/12 |  | djk; 11/21
| Given that the other player has submitted their turn when they made a valid simple move then I expect for it to be my turn. | [5 empty] | UD;11/12;Refer to above, thank |  | djk; 11/21
As a Player I want to take my opponent's checker on a move so I can improve my chances of winning. | Given that my opponent has a piece diagonally adjacent to one of my own when it is my turn then I expect to be able to jump my piece over theirs, capturing it. | [7 empty] | djk;11/21; can jump backwards
| Given that I am able to jump over at least one of my opponent's pieces when it is my turn then I expect that I will only be allowed to make a jump move instead of a simple move. | [7 empty] | djk;11/21; has some functionality, but sometimes does not let you complete a move you should be able to because it thinks there is an available jump move.
As a Player I want to take many of my opponent's checkers using multiple jump moves so I can improve my chances of winning. | Given that my opponent has their pieces aligned in such a way that one of my pieces can jump over multiple of theirs when it is my turn then I expect to have my piece be able to jump over all of their pieces, capturing them all in the process. | [7 empty] | djk;11/21; has some functionality, but allows the piece to move backwards without being kinged.
| Given that my opponent has their pieces aligned in such a way that one of my pieces can jump over multiple of theirs when it is my turn then I expect to only be able to submit a multiple jump move turn. | [7 empty] | djk;11/21; has some functionality, but sometimes does not let you complete a move you should be able to because it thinks there is an available jump move.
As a Player I want to King my checker so I can move both forward or backward on the board respectively. | Given I have reached my opponent's side of the board when I move my piece then I expect my normal piece to become a king piece. | [7 empty] | djk;11/21; it becomes a king visually, but not functionally
| Given I have a king piece that can make a valid move when it is my turn then I expect to be able to move towards the opponent's side of the board as well as my own. | [7 empty] | djk; 11/21; no functionality yet
As the user in WebCheckers I want to be able to forfeit so that I can terminate the game. | Given a player wants to resign when they click on the button to resign then they should expect the game to end and see a message. | [7 empty] | djk; 11/21
| Given a player wants to resign when they have made a valid move then the button should be disabled until they re-enter the Empty Turn state by waiting until their next turn or undoing their move. | [7 empty] | djk; 11/21; player can resign at any time
As a Player I want to request the rules so that I can understand how American Checkers is played. | Given I want to see the American Rules of Checkers when I click on the Player Help button then I expect a screen to appear showing me the American Rules of Checkers. | [7 empty] | djk; 11/21;Not yet implemented
| Given I am finished reading the American Rules of Checkers, when I click on a Close button then I expect to return to the screen I was previously on. | [7 empty] | djk; 11/21;Not yet implemented
As a player I want to be able to resign from a game | **Given** A player wants to resign **when** they have made a valid move **then** the button should be disabled until they re-enter the Empty Turn state by waiting until their next turn or undoing their move. | [7 empty] | djk; 11/21;Player can always enter the resign state
| Given A player wants to resign when they click on the button to resign then they should expect the game to end and see a message. | [7 empty] | djk; 11/21; It resigns the game for the player that clicks it, but does not end the game for their opponent.
As a player I want to be able to play against an AI opponent | **Given** It is an AI player's move **when** there is a space available **then** the AI player will calculate how well a move is. | [7 empty] | djk; 11/21;Not yet implemented
| **Given** No valid move **when** it is the AI player turn **then** the AI player will reach end of game state. | [7 empty] | djk; 11/21;Not yet implemented
| **Given** AI has done some calculation of a move **when** it is AI's turn **then** the AI player will select that move. | [7 empty] | djk; 11/21;Not yet implemented
| **Given** No valid move **when** it is the AI player turn **then** the AI player will reach end of game state. | [7 empty] | djk; 11/21;Not yet implemented
| **Given** A game is currently being played **when** it is my turn to move **then** there should be some way to know all where current players checker and opponent checkers are. | [7 empty] | djk; 11/21;Not yet implemented
| **Given** A board game **when** it is a player's turn **then** the end of game state should be known. | [7 empty] | djk; 11/21;Not yet implemented
| **Given** There are no valid moves for a player **when** it is a player's turn **then** the end of game state should be displayed | [7 empty] | djk; 11/21;Not yet implemented
As a player I want to be able to request a move for when I can't come up with my own | **Given** when you select request move **when** it is the current player's turn **then** a legal move will be displayed for the user to take. | [7 empty] | djk; 11/21;Not yet implemented